## 2024
Gant Chart Season Road Map 2024
TASK | Activity | % TASK | 2023-01-09 |  |  |  |  | 2023-02-13 |  |  |  | 2023-03-13 |  |  |  | 2023-04-10 |  |  |  | 2023-05-15 |  |  |  |  | 2023-06-12 |  |  |  | 2023-07-10 |  |  |  |  | 2023-08-14 |  |  |  | 2023-09-11 |  |  |  | 2023-10-09 |  |  |  |  | 2023-11-13 |  |  |  | 2023-12-11
ID |  | COMPLETE | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01
1 | Crop Stage (Cherry/Apple)
| Dormancy | 0%
| Bud Break | 0%
| Flowering | 0%
| Fruitlet | 0%
| Harvest | 0%
3 | Trials
| Snow Mold - Revelstoke | 50%
| Snow Mold- Salmon Arm | 50%
| Fertilizer Trial Work | 0%
| Apple Scab monitoring | 0%
0%
4 | Projects
| Herbicide Organic | 0%
| Sprayer Calbration Course | 20%
5 | Food Safety/Office Prep
| Food Safety Form Prep | 0%
| Employee Hiring | 0%
| Employee Training and Manual prep | 0%
| Take Annual Soil/Water Sample | 0%
| Internal Audit for GAP | 0%
| Book GAP Audit | 0%
6 | Orchard Activities
| Pruning | 0%
| Bud Mortality | 0%
| Fruit Bud Assessments | 0%
| Field Prep planting | 0%
| Scouting (bud stages, disease/pest) | 0%
| Irrigation | 0%
Hand Thinning
Soft Fruit Harvest, Packing, Sales
Pear Harvest
Apple Harvest
7 | Other Activities
Conference

## 1st Qtr
Jan 1- March 31 1st Quarter
TASK | Activity | Owner | Comment | 2023-01-08 |  |  |  |  | 2023-02-12 |  |  |  | 2023-03-12
ID |  |  |  | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26
1 | Crop Stage (Apple/Cherry)
Dormany
Bud Break | bar: 2023-03-12 to 2023-03-26
Flowering
1 | Food Safety Prep
| Binder/Drive Review | TO
| Grower File Preparation | TO
| Water Safety | TO, MT | TO to start
| Risk Assessment Update | TO
| Map Water | TO
| Water Req' for Testing | MT, TO
| Pricing Package | MT
| Pre-Payment Portion | MT
| Incentives | MT
| Costco new PHU req' | MT
| Review Pol/Proc Manual | MT
| Tesco Nurture Grasp/Leaf | MT
| PHU Assurance Letters | TO,MT
| Calibrate Machines | TO, MT | bar: 2023-03-26
| Take Soil Samples | TO | Extra cost? | bar: 2023-03-26
| Water Samples | TO | 3 sample total? | bar: 2023-03-26
4 | Projects
| Spornado | TO
| Send finalized quote | MT/TO | bar: 2023-01-29
| Create finalized project | MT/TO | bar: 2023-02-05 to 2023-03-26
| Ministry Spray Course | MT |  | 2023-03-05: Abbott; 2023-03-19: OK
Nutrient Management | bar: 2023-02-12 to 2023-02-19; 2023-03-05
5 | Trials
| Brevis Herbicide | TO | Review will be in 2nd Quarter | bar: 2023-03-26
| Snow Mold | TO | Snow coverage is good | bar: 2023-03-12 to 2023-03-26
Herbicide AgCanada (peaches) | bar: 2023-03-26
| Bidding | MT | bar: 2023-02-26 to 2023-03-26
6 | BC DAS | MT
| Factsheets | TO | bar: 2023-02-12 to 2023-02-26
| Contact L. King about format | TO | bar: 2023-01-29
Cherry Mildew | bar: 2023-03-12 to 2023-03-26
Pear Pyslla | bar: 2023-03-12 to 2023-03-26
San Jose Scale | bar: 2023-03-12 to 2023-03-26
Fireblight | bar: 2023-03-12 to 2023-03-26
Wooly Apple Aphid | bar: 2023-03-12 to 2023-03-26
Peach Borer | bar: 2023-03-12 to 2023-03-26
Codling Moth | bar: 2023-03-12 to 2023-03-26
Western Cherry Fruit Fly | bar: 2023-03-12 to 2023-03-26
BC DAS Meetings | bar: 2023-03-26
7 | Pearl Factsheets
GF-120 use
Bacterial vs fungal disease of apple
Cytospora vs pseudomonis cherry
Rodent and Bird Control
Terralink Tech Sheets
Cider Growing

## 2nd Qrt
April-June
TASK | Activity | START | DUE | DURATION | % TASK | 2023-07-08 |  |  |  |  | 2023-08-12 |  |  |  | 2023-09-09
ID |  | DATE | DATE | IN DAYS | COMPLETE | 2023-07-01 | 2023-07-08 | 2023-07-15 | 2023-07-22 | 2023-07-29 | 2023-08-05 | 2023-08-12 | 2023-08-19 | 2023-08-26 | 2023-09-02 | 2023-09-09 | 2023-09-16 | 2023-09-23
1
30%
0%
0%
0%
0%
2
0%
0%
0%
0%
0%
2.3 |  |  |  |  | 0%
2.4 |  |  |  |  | 0%
3
0%
0%
0%
0%
0%
0%
4
0%
0%
0%
0%
5
6
0%
0%
0%
0%
0%

## 3rd Qtr
Season 2023
TASK | Activity | START | DUE | DURATION | % TASK | 2023-07-08 |  |  |  |  | 2023-08-12 |  |  |  | 2023-09-09
ID |  | DATE | DATE | IN DAYS | COMPLETE | 2023-07-01 | 2023-07-08 | 2023-07-15 | 2023-07-22 | 2023-07-29 | 2023-08-05 | 2023-08-12 | 2023-08-19 | 2023-08-26 | 2023-09-02 | 2023-09-09 | 2023-09-16 | 2023-09-23
1
30%
0%
0%
0%
0%
2
0%
0%
0%
0%
0%
2.3 |  |  |  |  | 0%
2.4 |  |  |  |  | 0%
3
0%
0%
0%
0%
0%
0%
4
0%
0%
0%
0%
5
6
0%
0%
0%
0%
0%

## 4th Qtr
Season 2023
TASK | Activity | START | DUE | DURATION | % TASK | 2023-10-08 |  |  |  |  | 2023-11-12 |  |  |  | 2023-12-10
ID |  | DATE | DATE | IN DAYS | COMPLETE | 2023-10-01 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05 | 2023-11-12 | 2023-11-19 | 2023-11-26 | 2023-12-03 | 2023-12-10 | 2023-12-17 | 2023-12-24 | 2023-12-31
1
30%
0%
0%
0%
0%
2
0%
0%
0%
0%
0%
2.3 |  |  |  |  | 0%
2.4 |  |  |  |  | 0%
3
0%
0%
0%
0%
0%
0%
4
0%
0%
0%
0%
5
6
0%
0%
0%
0%
0%

## Task List
TASK | Activity | Owner | Comment | Complete?
ID
1 | Nutrient Management Workshops- Summerland
| Venue Booking Feb 21 | MT | St Stephens | DONE
| Insurance | MT | Co-operators | DONE
| Catering | MT | Send out headcount
| Factsheet from Apple/Cherry Workshop | MT
| Send out Save the Date | MT |  | DONE
| Review Stephen Content/Denise | MT
| Collect key from church week before | MT | Ask Trish- Linda is back | In Progress
| Evaluation 1 page | MT |  | DONE
| Creston |  | March 28th
| Book Venue | OT | Rec center or Rota Hall?
| Book Catering | OT | Golden Flour bakery | DONE
| Book Accomedation | OT | 1 room with 2 Queens - Mar 27 and Mar 28th | DONE
| IAF Poster/Official invite/Eventbrite | IAF |  | DONE